## Self-Assessment Matrix
Resilient Recovery Roadmap |  |  | Program Implementation Self-Assessment | [5 empty] | Assessment Validation
|  |  | Not Identifiable | Limited Activity | Active Program | Robust Program | Best Practice |  | Document in 1-3 sentences why you chose that score.
Roadmap | Recommended Activities | Suggested Elements | 0 | 1 | 2 | 3 | 4
Part 1: Organizing | Organize Local Leadership | Champions identified and engaged in program |  |  |  | 3 |  | 1 | [Use this space to provide a few sentences about why you chose this score. Please provide specifics about programs, activites, and efforts that support the scoring]
| Involve the Whole Community | Whole Community representatives identified and engaged |  |  |  |  | 4 | 1
| Establish Coordination Methods | Voluntary Organizations Active in Disaster (VOAD) developed and engaged |  |  | 2 |  |  | 1
|  | Local Emergency Planning Committees |  |  | 2 |  |  | 1
|  | Community Resilience Committees |  | 1 |  |  |  | 1
Part 2: Recovery Planning | Assess Capabilities and Threats | Stakeholder Preparedness Review (SPR) |  |  | 2 |  |  | 1
|  | Threat and Hazard Identification and Risk Assessment (THIRA) |  |  | 2 |  |  | 1
|  | Hazard Vulnerability Assessment |  |  | 2 |  |  | 1
| Create Recovery Plans | Long-Term Recovery Plan developed |  | 1 |  |  |  | 1
|  | Metrics for successful recovery established |  | 1 |  |  |  | 1
|  | Recovery goals determined |  | 1 |  |  |  | 1
| Integrate Hazard Mitigation with Recovery | Mitigation actions integrated with recovery programs | 0 |  |  |  |  | 1
| Prioritize Projects | Recovery priorities determined |  |  | 2 |  |  | 1
|  | Additional prioritization considerations |  |  |  | 3 |  | 1
| Implement Resilient Systems | Implementing resilient systems approach |  |  | 2 |  |  | 1
| Integrate Approach to Recovery Programs | Implementing integrated recovery approach |  | 1 |  |  |  | 1
Part 3: Managing Recovery Programs | Identify Recovery Staffing | Recovery staffing identified |  |  | 2 |  |  | 1
| Manage Financials | Finance Department engaged in recovery programs |  |  |  | 3 |  | 1
|  | Recovery financial plan developed |  | 1 |  |  |  | 1
|  | Supporting Whole Community financial resilience | 0 |  |  |  |  | 1
| Leverage Available Resources | Existing recovery resources identified and engaged |  |  | 2 |  |  | 1
| Pursue Grant Opportunities | FEMA grant opportunities assessed |  |  |  | 3 |  | 1
|  | Other grant opportunities assessed |  |  |  | 3 |  | 1
|  | Application developed/submitted |  |  | 2 |  |  | 1
| Implement Improvement Process | Improvement process implemented |  |  | 2 |  |  | 1
|  | Determined recovery program success factors |  |  |  | 3 |  | 1
|  | Regularly assess progress and implement improvements |  | 1 |  |  |  | 1
Total: |  |  | 0 | 7 | 22 | 18 | 4
Recovery Program Self-Assessment Score * | [5 empty] | 27 | 1.8889
* A score of 2 indicates an active recovery program. The score is determined by adding up the value of all of the indicated elements and dividing that number by the total number of elements.

## Improvement Targets
Resilient Recovery Roadmap - Improvement Plan
Jurisdiction: | County A | Assessment Completed By: | EMA Director | Date: | 2022-12-01
Roadmap Element | Improvement Target | Implementation Approach | Responsible Organization | Completion Target Date | Funding Source | Priority
Create Recovery Plans | Develop a Long-Term Recovery Plan that established goals and metrics for successful recovery by the completion of the RRC Recovery Planning Workshop. | Attend RRC Recovery Workshops, Participate in the Recovery Technical Assistance, Promote Recovery with peers and potential stakeholders. | EMA | 2024-06-01 | Hazard Mitigation Grant Program (HMGP) | 1
Integrate Mitigation Actions with Recovery Programs | While developing the Pre-Disaster Recovery Plan with the RRC Workshop (2023-2024), review the Hazard Mitigation Plan (HMP) actions and align as many of the activities as possible to identify efficiencies in funding, staffing, and resources. | Review the HMP mitigation actions in a joint session with the Long-Term Recovery Committee (LTRC) and Local Emergency Planning Committee (LEPC). Identify common efforts and align priorities. Update the HMP and the LTRP accordingly. | EMA | 2024-12-01 | Hazard Mitigation Grant Program (HMGP) | 2
Manage Financial Recovery | Develop a Financial Recovery Plan that that involves the finance department and support the whole community resilience by the completion of the RRC Financial Recovery Program. | Participate in the RRCs Financial Recovery Program. | Finance | 2024-06-01 | Hazard Mitigation Grant Program (HMGP) | 3
Pursue Grant Opportunities | Identify, assess, and apply for state and federal grant opportunities that are offered to municipalities in support of mitigation and recovery goals, during the 2023-24 grant cycle. | Discuss local mitigation needs with multiple departments and select the most appropriate grant path. Participate in the RRC Grant workshops. | Finance | 2024-12-01 | Building Resilient Infrastructure and Communities (BRIC) | 4
5
6
7
8